## Sheet1
Task Name | Resource | Start | End | Days | Status
Project planning |  | 2018-03-06 | 2018-03-07 | 1 | Complete
Project scinario |  | 2018-03-06 | 2018-03-06 | 0 | Complete
Identify requirments |  | 2018-03-06 | 2018-03-07 | 1 | Complete
User stories |  | 2018-03-06 | 2018-03-07 | 1 | Complete
Features description |  | 2018-03-06 | 2018-03-07 | 1 | Complete
schedule |  | 2018-03-06 | 2018-03-07 | 1 | Complete
Sprint 1 |  | 2018-03-07 | 2018-03-14 | 7
features description | Tascks | 2018-03-06 | 2018-03-07 | 1 | Complete
login | Analysis | 2018-03-06 | 2018-03-06 | 0 | Complete
| Design | 2018-03-06 | 2018-03-06 | 0 | Complete
| Creating database | 2018-03-07 | 2018-03-07 | 0 | Complete
| Creating GUI | 2018-03-07 | 2018-03-07 | 0 | Complete
Schedul
Date | Event
6 March, Tuesday 5:00 pm | Project set-up and roles assigned
7:14 March | 1st Sprint
2018-03-11 | Reversal Sprint Review Meeting for Sprint 1
2018-03-13 | Sprint Review Meeting For Sprint 2
15:22 March | 2nd sprint
2018-03-19 | Reversal Sprint Review Meeting for Sprint 1
2018-03-21 | Sprint Review Meeting For Sprint 2
23:30 March | 3rd sprint
2018-03-27 | Reversal Sprint Review Meeting for Sprint 1
2018-03-29 | Sprint Review Meeting For Sprint 2